## Serbia
I. Identify and define organisation(s) and internal structure
Activity |  | Begin date | End date | Order | Players | Outcome | Product
a. |  | January 13 | March 31 |  | Ivana (IES) and Gajin (RCUB) | A provisional text that will define roles and obligations of partners, appx one page. | Charter document
b. | Define organisation(s) and scope of collection | January 13 | March 31 |  | Aleksandra, Ivana and Aleksandar | One or two page text, to combine with previous document, with a section "scope of collection"
c. | Establish the set of services to be provided | January 13 | March 31 |  | Aleksandra, Ivana and Aleksandar | One-page text, to combine with previous document, with a section "set of services"
d. | Develop a sustainable financing scheme and budget | April 1st | May 31 |  | Aleksandra & Aleksandar, support from CESSDA partners | Detailed budget | Budget document
e. | Develop a governance structure (e.g. oversight board, scientific board, meetings per year, procedural rules) | January 13 | March 31 |  | IES & ISS | Internal documents which will guarantee wide independence and arrange governance structure | Charter document
f. | Create a classification scheme of data types to be archived (according to risk level) and corresponding distribution mechanisms | [5 empty] | Integrated as point b. in part IV of EP
g. | Define stakeholders and partner institutions, with their roles and limitations | January 13 | March 31 |  | Aleksandar | One-page text, to include in charter document, with a section "Stakeholders". Not as important for WP5 | Charter document
h. | Establish formal communication channels with and between stakeholders and partner institutions(mailing list) | March 1st | March 31 |  | Ivana | Database of researchers, institutions, fields of research and e-mail addresses | (Be aware of misuse of confidential information)
i. | Define internal structure of organisation, including an organisational chart | January 13 | March 31 |  | Aleksandra, Ivana and Aleksandar | Connect with governance structure within Charter document | Charter document
j. | Identify work space/facility | January 13 | March 31 |  | Aleksandra, Ivana and Aleksandar & Gajin (RCUB) | The same as previous | Charter document
k. | Create institutional brand and logo (collaborative) | January 13 | March 31 |  | Perhaps subcontracting for all three countries | Brand and logo. | Charter document
l. | Create website (collaborative) | April 1st | May 23 |  | Content: Aleksandra, Ivana and Anja. Support from tech group and country tech subgroups. Help from CESSDA partners. |  | Institutional website
m. | Begin promotional activities to establish continuous visibility among key stakeholders (meetings, workshops, email and letter campaigns) | January 6 | January 31 |  | Aleksandra | Plan of promotional activities | (IES junior researchers will search for nice opportunities for promotional activities and data from researchers, prepare answers on potential questions, etc)
II. Human Resources
Activity |  | Begin date | End date | Order | Players | Outcome | Product
a. | Define minimum number of staff (size) needed and roles and responsibilities for likely staff positions (i.e. who does what) | January 13 | March 31 |  | FORS for generic part, IES for local tailoring | Description of roles and responsibilities for expected staff positions | "Roles, responsibilities, and training of staff" document
b. | Prepare job descriptions, advertise, interview, issue contracts (near to "day one" once funding has been secured) and/or incorporate responsibilities into existing positions |  |  |  |  | No high priority, can be done later
c. | Develop knowledge and skills of staff through ongoing training (part-generic) | January 13 | March 31 |  | FORS, with local tailoring | Same document as Roles and Responsibilities: include Cessda, iassist, workshops, learning technique and standards | "Roles, responsibilities, and training of staff" document
d. | Define institutional rules and regulations for staff (e.g. regarding sick leave) (but only needed if a new institution is envisioned)
IV. Establish policies, quality control procedures, and workflows
Activity |  | Begin date | End date | Order | Players | Outcome | Product
a. | Establish data policies and written protocols for data management and access | January 13 | March 31 |  | FORS, with support from CESSDA partners, and local tailoring | Data quality policy: body document + country specific annex. Policy document: "Data management and access" | "Data policy and procedures" document
b. | Create a classification scheme of data types to be archived (according to risk level) and corresponding distribution mechanisms | January 13 | March 31 |  | IES, with support from FORS | Data classification scheme | "Data policy and procedures" document
c. | Develop policy and plans for data backup and security | January 13 | March 31 |  | FORS, with support from CESSDA partners, and local tailoring | Security and backup: generic part + country specific annex. Document: "Backup and security policy and procedures" | "Data policy and procedures" document
d. | Ensure standardisation of policy and tools (including compliance with CESSDA, DAS and international standards) (generic) | January 13 | March 31 |  | FORS (with help from Hilary) | Statement of intent. Document: "Ensuring best practice, standardisation, and international data sharing" | "Data policy and procedures" document
e. | Study legal background and develop contracts (part-generic) | January 13 | March 31 |  | IES, with support from FORS | Document: "Legal background and contracts" | "Data policy and procedures" document
f | Establish list of potential data sources | March 1 | April 30 |  | IES | Identification of relevant available datasets | "List of potential data providers"
g. | new activity: prepare 2-3 data sets to promote DS, connected to website and promotional activities | April 1 | May 23 |  | IES | Documented datasets | Datasets accessible on website
h. | Develop guides for researchers and training events to promote good practice and data sharing (generic) | April 1 | June 30 |  | FORS for the guides, with local support and collaboration; UKDA for training event, tailored locally. | Guides and a planned training event for after day one | Online tutorials for data producers and users, and one training event
i | Develop basic performance monitoring system (i.e. indicators, measures for monitoring change over time) (part-generic) | April 1 | June 30 |  | FORS (UKDA, SLO), with local tailoring | Set of indicators and measures | "Performance monitoring system"
j | Create database of users and data producers -> client database | January 13 | February 28 |  | IES | List of clients | Database for promotional activities

## Gantt Chart Serbia
|  | January | [30 empty] | February | [27 empty] | March | [29 empty] | April | [29 empty] | May
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
a. | Identify organisation(s) to assume the data service | bar: February 1 to February 20
b. | Define organisation(s) and scope of collection | bar: February 1 to February 20
c. | Establish the set of services to be provided | bar: February 1 to February 20
d. | Develop a sustainable financing scheme and budget | bar: April 1 to May 31
e. | Develop a governance structure (e.g. oversight board, scientific board, meetings per year, procedural rules)
f. | Create a classification scheme of data types to be archived (according to risk level) and corresponding distribution mechanisms
g. | Define stakeholders and partner institutions, with their roles and limitations | bar: March 1 to March 15
h. | Establish formal communication channels with and between stakeholders and partner institutions(mailing list) | bar: March 1 to March 20
i. | Define internal structure of organisation, including an organisational chart | bar: February 1 to March 20
j. | Identify work space/facility | bar: February 1 to March 20
k. | Create institutional brand and logo
l. | Create website (part-generic)
m. | Begin promotional activities to establish continuous visibility among key stakeholders (meetings, workshops, email and letter campaigns) | bar: January 1 to January 31
II. Human Resources
Activity
a. | Define minimum number of staff (size) needed and roles and responsibilities for likely staff positions (i.e. who does what) | bar: January 15 to February 20
b. | Prepare job descriptions, advertise, interview, issue contracts (near to "day one" once funding has been secured) and/or incorporate responsibilities into existing positions | bar: January 15 to March 15
c. | Develop knowledge and skills of staff through ongoing training (part-generic)
d. | Define institutional rules and regulations for staff (e.g. regarding sick leave) (but only needed if a new institution is envisioned)
IV. Establish policies, quality control procedures, and workflows
Activity
a. | Establish data policies and written protocols for data management and access (generic) | bar: January 15 to February 15
scope and types of data to be included in the archive | bar: January 15 to February 15
workflow for ingest and treatment | bar: January 15 to February 15
guidelines data depositors | bar: January 15 to February 15
b. | Create a data archiving plan (part-generic)
list of research projects
letters to be sent to project leaders
c. | Develop policy and plans for data backup and security (part-generic) | bar: January 15 to February 28
d. | Ensure standardisation of policy and tools (including compliance with CESSDA, DAS and international standards) (generic) | bar: January 15 to February 28
identify relevant existing standards | bar: January 15 to February 28
evaluation of poicies and practices | bar: January 15 to February 28
what can be done to bring data service closer to international standards | bar: January 15 to February 28
e. | Develop guides for researchers and training events to promote good practice and data sharing (generic) | bar: March 1 to March 30
promotional material | bar: March 1 to March 30
workshop on data management | bar: March 1 to March 30
guidelines for data depositors | bar: March 1 to March 30
f. | Study legal background and develop contracts (part-generic) | bar: March 1 to March 30
update work of WP2 | bar: March 1 to March 30
summarise national law and its implication for the data service | bar: March 1 to March 30
licences for data deposit and data use | bar: March 1 to March 30
g. | Develop basic performance monitoring system (i.e. indicators, measures for monitoring change over time) (part-generic) | bar: February 15 to March 30
h. | Create database of users (generic) -> client database? | bar: January 15 to April 1
i. | Create database of researchers (part-generic) -> client database? | bar: January 15 to April 1